## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to project | MUST HAVE | No Dependency | K.Pavithra | 3- Completed
S1 | S1 | US-001 | About Statistical Models | MUST HAVE | No Dependency | K.Pavithra | 2- In Progress
S1 | S1 | US-001 | Continuation of Statistical Models | MUST HAVE | No Dependency | K.Pavithra | 3- Completed
S1 | S1 | US-001 | Chi-square test | MUST HAVE | No Dependency | K.Pavithra | 3- Completed
S2 | S2 | US-001 | Explanation about NLP | MUST HAVE | Google colab | K.Pavithra | 3- Completed
S3 | S3 | US-001 | How to load files to Notebook | MUST HAVE | Google colab | K.Pavithra | 2- In Progress
S3 | S3 | US-001 | Continuation of loading files | MUST HAVE | Google colab | K.Pavithra | 3- Completed
S4 | S4 | US-001 | Introduction to RAG | MUST HAVE | Google colab | K.Pavithra | 2- In Progress
S4 | S4 | US-001 | Introduction to LangChain | MUST HAVE | Google colab | K.Pavithra | 2- In Progress
S4 | S4 | US-001 | Loading the Pdf file and introducing Groq API | SHOULD HAVE | Groq cloud | K.Pavithra | 2- In Progress
S5 | S5 | US-001 | creating an API Token | SHOULD HAVE | Groq cloud | K.Pavithra | 3- Completed
S5 | S5 | US-001 | Dividing to chunks and embeddings | MUST HAVE | Google colab | K.Pavithra | 3- Completed
S6 | S6 | US-001 | Introducing the model and creating env file | MUST HAVE | Google colab | K.Pavithra | 3- Completed
S6 | S6 | US-001 | Introduction to pandas AI agent | MUST HAVE | Google colab | K.Pavithra | 3- Completed
S7 | S7 | US-001 | Implementing the Interface | MUST HAVE | Streamlit | K.Pavithra | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7